## Sheet1
October
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
| 1 | 2 | 3 | 4 | 5 | 6
7 | 8 | 9 | 10 | 11 | 12 | 13
|  | Meeting | IMY 220 A6 | IMY 220 EO | Finish UML | Register Teams*
14 | 15 | 16 | 17 | 18 | 19 | 20
Finishing touches* |  | Feedback* |  | Finilize UML | Skeleton code | COS 226 A2
21 | 22 | 23 | 24 | 25 | 26 | 27
COS 214 EO3 | Basic code | Feedback |  | COS 284 CT
28 | 29 | 30 | 31
Advanced code |  | Feedback
November
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
|  |  |  | 1 | 2 | 3
|  |  |  | Finilize project |  | IMY 220 Project
4 | 5 | 6 | 7 | 8 | 9 | 10
Submit project | Demo | Demo
11 | 12 | 13 | 14 | 15 | 16 | 17
18 | 19 | 20 | 21 | 22 | 23 | 24
25 | 26 | 27 | 28 | 29 | 30
1. 13 October - Team registration of 5 to 7 members to be completed. Assign a team lead. Complete this registration on the CS portal | [6 empty] | Done*
2. 15 October - Submit initial project design (Practical 6) | [6 empty] | Done*
3. 15 and 16 October - Get initial design marked and receive feedback | [6 empty] | Done*
4. 22 and 23 October - Demonstrated updated initial design (if necessary) and skeleton implementation | [6 empty] | Busy
5. 29 and 30 October - Review minimal viable project and receive feedback | [6 empty] | No there yet
6. 4 November - Submission of project on ClickUP. | [6 empty] | No there yet
7. 5 and 6 November - Project demos. | [6 empty] | No there yet